## Sheet1
WEEKLY Tasks | day 1 | day 2 | day 3 | day 4 | day 5 | day 6 | day 7 | Estimated Hours | Actual hours (total)
Revise Draft Prototype | day 1: 0; day 3: 0; day 6: 4 | 2 | 4
Plan Scrum & Sprints | day 2: 0; day 3: 0 | 2 | 0
Materials for Prototype | [7 empty] | 1 | 2 | bar: day 1 to day 7
Meeting with Professor | day 5: 0 | 0 | 0
Meet with Team | day 5: 0 | 0 | 0
Draft Innovation Brief | day 6: 0 | 0 | 0
Total Hours | 0 | 0 | 0 | 1 | 0 | 4 | 1 | 5 | 6
Tasks Completed | 0 |  | 0 | 1 |  | 1 | 1 | 4
Hours Remaining (ideal) | 4.2857 | 3.5714 | 2.8571 | 2.1429 | 1.4286 | 0.71429 | 0 | 5
Tasks Completed (ideal) | 0.57143 | 1.1429 | 1.7143 | 2.2857 | 2.8571 | 3.4286 | 4 | 4
Hours Remaining (actual) | 5 | 5 | 5 | 4 | 4 | 0 | -1
Tasks Completed (actual) | 0 | 0 | 0 | 1 | 1 | 2 | 3
fill these in at the beginning of the week
fill these in daily, as you go
don't touch these cells; they are doing calculations
Note on A3: Put the names of your tasks here
Note on B3: Put the number of hours you spent working on each task here, for each day of the week
Note on I3: Estimate how long each task will take to complete here, for each task
Note on B9: Fill in the number of tasks that you complete each day
Note on I11: Put the number of tasks you have, here.